: 27/07/2026

: sanjay.goyal@zeppelin.com
: +91-9755945046

Date

Email 
Phone

To,

M/s JK Tyre & Industries Ltd

Laksar, Uttarakhand

Kind Attention: Mr. Ajay Aswal

Dear Sir,

Subject: Offer for MES for Unit 2 & Unit 4

As per the discussion and details received over email with the technical team on the MES requirement understanding. The enclosed offer is having all the technical details.

In case you need any further clarifications, please feel free to call us at any time convenient to you.

Thanking you and assuring you of our best attention at all times.

Yours truly,

Sanjay Goyal

Head of MES, Digital Manufacturing

Smart Controls India Limited

Technical Offer

Offer Number	:

Customer		: JK
End Customer	: LTP

Project			: MES – Unit 2 & Unit 4

Table of Contents

2	Terms and Abbreviations	4

3	Basis Of Offer	5

3.1	Revision History	5

3.2	Functional Overview	5

3.3	Plant Location	5

3.4	Machine Details	5

4	Functional Details	5

4.1	Solution Architecture	5

4.2	IT Architecture	5

5	Scope Of Work	5

5.1	Key Deliverables	5

5.2	Scope Of Service	5

5.3	Scope Of Supply	5

5.3.1	Basis Of Supply	6

5.3.2	Bill Of Material	6

5.4	Scope of Work RACI	6

6	Project Management	6

6.1	Project Organization Structure	6

6.2	Project Governance	6

6.3	Project Phases and Deliverables	6

6.3.1	Requirement Freeze & Workshop	7

6.3.2	Functional Design Session	7

6.3.3	System Integrated Testing (SIT)	7

6.3.4	User Acceptance Testing (UAT)	8

6.3.5	Commissioning & Go Live	8

6.3.6	Rollout and Handover	8

6.4	Project Timelines	9

7	Project Understanding	9

7.1	General Assumptions	9

7.2	Project Assumptions	9

7.3	Customer Support	9

7.4	Exclusions	9

8	Change Request Procedure	10

8.1	Change in Scope Of Service	11

8.2	Change in Scope Of Supply	11

9	Acceptance Procedures	12

9.1	Notification of Deliverable Available Date	12

9.2	User Acceptance Tests	12

9.3	Inspection and Acceptance of Deliverables by Customer	12

# Terms and Abbreviations

| Terms | Definition |
| --- | --- |
| SCIL | Smart Controls India Ltd |
| CUSTOMER/ CUST | JK |
| END CUSTOMER /ECST | JK - LTP |
| BRD | Business Requirement Document |
| MES | Manufacturing Execution System |
| SmartMES | Smart Controls Manufacturing Execution System platform |
| ERP | Enterprise resource planning |
| WMS | Warehouse Management System |
| PLC | Programmable Logic Controller |
| SCADA | Supervisory Control and Data Acquisition |
| RM | Raw Material |
| PO | Purchase order |
| GRN | Goods Received Note |
| OEM | Original Equipment Manufacturer |
| NCM | Non-Conformity Material |
| HMI | Human Machine Interface |
| BOM | Bill Of Material |
| OPC | Open Platform Communications |
| DB | Database |
| CMMS | Computerized Maintenance Management System |

# Basis Of Offer

This document is SCIL’s confidential and proprietary. SCIL provides this document to CUSTOMER with the understanding that its contents will be held in strict confidence and will not be duplicated or used in whole or in part for any purpose other than evaluation of this response, without prior written consent from SCIL.

This document reflects SCIL’s understanding of business needs and project requirements and was prepared based on the information available at that point in time. Any changes to these needs or requirements may require changes to any portion of this offer.

Any information related to potential future product functionality should not be construed as a guarantee or commitment on the part of SCIL to develop and/or deliver such functionality.

This information does not constitute an offer. Neither party will have any contractual commitment to the other until a definitive written contract has been negotiated and signed by the parties referring to this offer as technical and commercial scope.

## Revision History

First Draft, R0, 27-07-2026

## Functional Overview

Smart Controls India Limited (SCIL) proposes to implement a Manufacturing Execution System (MES) covering the tyre manufacturing operations of JK Tyre – Laksar Tyre Plant (LTP) for Unit‑2 and Unit‑4. The offer covers shopfloor data acquisition from the existing and planned machines of both units, the manufacturing operations management layer, and the interfaces to the customer’s existing enterprise applications. The solution is delivered on SmartMES, the Smart Controls manufacturing execution platform; no third party MES platform license is included in this offer.

The solution is structured in the following layers:

- Layer 2 – SCADA: TBM SCADA, Curing SCADA and Plantwide SCADA for machine connectivity, shopfloor data acquisition, visualisation and operator interface.

- Layer 3 – Manufacturing Operations Management: MES for production execution, material and product traceability and in‑process quality management.

- Interfaces: Integration with the customer’s existing third party systems (ERP, WMS, ASRS and OEM systems) through mutually agreed interface definitions.

The detailed functional scope of each module shall be frozen during the Requirement Freeze & Workshop phase and documented in the Business Requirement Document (BRD) as described in the Project Management section of this document.

## Plant Location

JK – LTP, Laksar Uttarakhand

## Machine Details

The machine population considered for this offer is based on the machine data shared by the customer in “Machine Details Data Unit‑2 Unit‑4_V6.xlsx”. A total of 145 machines are covered – 42 in Unit‑2 and 103 in Unit‑4 – as summarised below.

| Unit | Process Area | No. of Machines | PLC Available | PLC Not Available | To Be Confirmed |
| --- | --- | --- | --- | --- | --- |
| Unit‑2 | TBB Tyre Building | 29 | 29 | – | – |
| Unit‑2 | LCV Tyre Building | 13 | 13 | – | – |
| Unit‑2 | Sub Total | 42 | 42 | – | – |
| Unit‑4 | CFE 1 | 3 | 3 | – | – |
| Unit‑4 | CFE 2 | 4 | 4 | – | – |
| Unit‑4 | 2 Roll Calender ‑1 | 2 | 2 | – | – |
| Unit‑4 | 2 Roll Calender ‑2 | 1 | 1 | – | – |
| Unit‑4 | 2 Roll Calender ‑3 | 1 | 1 | – | – |
| Unit‑4 | 3 Roll Calender ‑3 | 1 | 1 | – | – |
| Unit‑4 | Bias Cutter | 3 | 3 | – | – |
| Unit‑4 | Bead Winding | 2 | 2 | – | – |
| Unit‑4 | Fabric Cutter | 3 | 3 | – | – |
| Unit‑4 | Building | 45 | 39 | 6 | – |
| Unit‑4 | Curing | 8 | 8 | – | – |
| Unit‑4 | Balancing | 10 | 10 | – | – |
| Unit‑4 | Runout | 11 | 11 | – | – |
| Unit‑4 | 2nd Line Inspection | 9 | – | – | 9 |
| Unit‑4 | Sub Total | 103 | 88 | 6 | 9 |
| Total | Unit‑2 and Unit‑4 | 145 | 130 | 6 | 9 |

Table: Summary of machines considered in scope – Unit‑2 and Unit‑4

### Unit‑2 – Machine Details

| S.No | Process Area | Machine Group | Qty | PLC Make | PLC Model | Existing Communication | Recommended Interfacing Hardware | SmartMES Communication |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | TBB Tyre Building | J‑1 to J‑25, J‑54 to J‑56 | 28 | Mitsubishi | FX2N‑64MR | RS232 (Mini DIN) | OEM Ethernet Communication Module | Kepware OPC Server (Mitsubishi Ethernet Driver) |
| 2 | TBB Tyre Building | OTR‑1 | 1 | Allen‑Bradley | SLC500 | RS232 | OEM Ethernet Communication Module | Kepware OPC Server (Allen‑Bradley Ethernet Driver) |
| 3 | LCV Tyre Building | AMCL‑1 to AMCL‑6 | 6 | Mitsubishi | FX2N‑64MR | RS232 (Mini DIN) | OEM Ethernet Communication Module | Kepware OPC Server (Mitsubishi Ethernet Driver) |
| 4 | LCV Tyre Building | LNT‑1 to LNT‑5 | 5 | Mitsubishi | FX2N‑64MR | RS232 (Mini DIN) | OEM Ethernet Communication Module | Kepware OPC Server (Mitsubishi Ethernet Driver) |
| 5 | LCV Tyre Building | AMCL‑7 & AMCL‑8 | 2 | Mitsubishi | FX5U | Built‑in Ethernet | Use built‑in Ethernet port | Kepware OPC Server (Mitsubishi Ethernet Driver) |
|  | Total |  | 42 |  |  |  |  |  |

Table: Unit‑2 machine and control system details

On the FX2N and SLC500 machines the RS232 port is occupied by the HMI, so no external communication port is free; the recommended OEM Ethernet communication module addresses this. Programming software required for these machines is GX Developer (Mitsubishi) and RSLogix (Allen‑Bradley).

The interfacing hardware recommended for each controller type in Unit‑2 is given below. Final selection is to be confirmed against the installed hardware configuration of each machine during the Functional Design phase.

| Process Area | PLC Make | PLC Model | Recommended Hardware | Kepware Connectivity | Remarks |
| --- | --- | --- | --- | --- | --- |
| TBB / LCV | Mitsubishi | FX2N‑64MR | Mitsubishi FX2NC‑ENET‑ADP (Ethernet Adapter) or an OEM‑compatible Ethernet communication solution for the installed FX2N configuration | Mitsubishi Ethernet Driver | Mitsubishi documentation shows Ethernet adapters for FX2N‑family controllers, but implementation depends on the installed hardware configuration. |
| TBB | Allen‑Bradley | SLC500 | 1747‑AENTR EtherNet/IP Adapter | Allen‑Bradley Ethernet Driver | Provides EtherNet/IP connectivity for SLC500 systems. |
| LCV | Mitsubishi | FX5U | No communication module required. Use the built‑in Ethernet and isolate it using an Industrial NAT device. | Mitsubishi Ethernet Driver | This is the preferred architecture unless the customer specifically requires an additional Ethernet network module. |

Table: Unit‑2 recommended interfacing hardware

### Unit‑4 – Machine Details

| S.No | Process Area | Machine No. | PLC Available | PLC Make | PLC Model | Remark |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | CFE 1 | Cold Feed Extruder‑1 (LINE) | Yes | Siemens | 315‑2‑DP |  |
|  | CFE 1 | Cold Feed Extruder‑1( EXTRUDER) | Yes | Siemens | 313C‑2DP |  |
|  | CFE 1 | Cold Feed Extruder‑1 (SKIVER) | Yes | Siemens | 313C‑2DP |  |
| 2 | CFE 2 | Cold Feed Extruder‑2( LINE) | Yes | Siemens | 315‑2‑DP |  |
|  | CFE 2 | Cold Feed Extruder‑2 (EXTRUDER) | Yes | Siemens | 313C‑2DP/1214PN |  |
|  | CFE 2 | Cold Feed Extruder‑2 (CUSHION CALENDER) | Yes | Siemens | 313C‑2DP |  |
|  | CFE 2 | Cold Feed Extruder‑SKIVER | Yes | Siemens | 313C‑2DP | Machine upgradation work is ongoing |
| 3 | 2 Roll Calender -1 | 2 Roll Calender | Yes | Siemens | 313C‑2DP |  |
|  | 2 Roll Calender -1 | 2 Roll Calender (line) | Yes | Siemens | 313C‑2DP |  |
| 4 | 2 Roll Calender -2 | 2 Roll Calender | Yes | Siemens | 1515‑2PN |  |
| 5 | 2 Roll Calender -3 | 2 Roll Calender | Yes | Siemens | 313C‑2DP |  |
|  | 3 Roll Calender -3 | 2 Roll Calender ‑line | Yes | Siemens | 313C‑2DP |  |
| 6 | Bias Cutter | Bias Cutter ‑1 | Yes | Siemens | S7‑300 (313‑C‑2DP) |  |
| 7 | Bias Cutter | Bias Cutter ‑2 | Yes | Siemens | S7‑300 (313‑C‑2DP) |  |
| 8 | Bias Cutter | Bias Cutter ‑3 | Yes | Siemens | S7‑300 (313‑C‑2DP) |  |
| 9 | Bead Winding | Bead Winding‑1 | Yes | Mitsubishi | FX3U‑64MR |  |
| 10 | Bead Winding | Bead Winding‑2 | Yes | Mitsubishi | FX2N‑64MR |  |
| 11 | Fabric Cutter | Multislitter | Yes | Siemens | S7‑200 (224‑DC/DC/DC) |  |
| 12 | Fabric Cutter | Long Cutter | Yes | Mitsubishi | FX3G‑24M |  |
| 13 | Fabric Cutter | Multislitter | Yes |  |  | New Machine |
| 14 | Building | STU‑1 | Yes | Mitsubishi | FX2N‑84MR |  |
| 15 | Building | STU‑2 | Yes | Mitsubishi | FX5U‑84MT |  |
| 16 | Building | STU‑3 | Yes | Mitsubishi | FX2N‑84MR |  |
| 17 | Building | STU‑4 | Yes | Mitsubishi | FX2N‑84MR |  |
| 18 | Building | STU‑5 | Yes | Mitsubishi | FX2N‑84MR |  |
| 19 | Building | STU‑6 | Yes | Mitsubishi | FX2N‑84MR |  |
| 20 | Building | STU‑7 | Yes | Mitsubishi | FX2N‑84MR |  |
| 21 | Building | STU‑8 | Yes | Mitsubishi | FX2N‑84MR |  |
| 22 | Building | STU‑9 | Yes | Mitsubishi | FX2N‑84MR |  |
| 23 | Building | STU‑10 | Yes | Mitsubishi | FX2N‑84MR |  |
| 24 | Building | STU‑11 | Yes | Mitsubishi | FX2N‑84MR |  |
| 25 | Building | STU‑12 | Yes | Mitsubishi | FX2N‑84MR |  |
| 26 | Building | STU‑13 | Yes | Mitsubishi | FX2N‑84MR |  |
| 27 | Building | STU‑14 | Yes | Mitsubishi | FX2N‑84MR |  |
| 28 | Building | STU‑15 | Yes | Mitsubishi | FX2N‑84MR |  |
| 29 | Building | BTU‑16 | Yes | Mitsubishi | FX2N‑84MR |  |
| 30 | Building | STU‑17 | Yes | Mitsubishi | FX2N‑84MR |  |
| 31 | Building | STU‑18 | Yes | Mitsubishi | FX2N‑84MR |  |
| 32 | Building | STU‑19 | Yes | Mitsubishi | FX2N‑84MR |  |
| 33 | Building | STU‑20 | Yes | Mitsubishi | FX2N‑84MR |  |
| 34 | Building | STU‑21 | Yes | Mitsubishi | FX2N‑84MR |  |
| 35 | Building | STU‑22 | Yes | Mitsubishi | FX2N‑84MR |  |
| 36 | Building | STU‑23 | Yes | Mitsubishi | FX2N‑84MR |  |
| 37 | Building | BTU‑24 | Yes | Mitsubishi | FX2N‑84MR |  |
| 38 | Building | BTU‑25 | Yes | Mitsubishi | FX2N‑84MR |  |
| 39 | Building | BTU‑26 | Yes | Mitsubishi | FX2N‑84MR |  |
| 40 | Building | BTU‑27 | Yes | Mitsubishi | FX2N‑84MR |  |
| 41 | Building | STU‑28 | Yes | Mitsubishi | FX2N‑84MR |  |
| 42 | Building | STU‑29 | Yes | Mitsubishi | FX2N‑84MR |  |
| 43 | Building | STU‑30 | Yes | Mitsubishi | FX2N‑84MR |  |
| 44 | Building | STU‑31 | Yes | Mitsubishi | FX2N‑48MR |  |
| 45 | Building | STU‑32 | Yes | Siemens | S7‑1200 (1214C‑DC/DC/DC) |  |
| 46 | Building | STU‑33 | Yes | Siemens | S7‑1200 (1214C‑DC/DC/DC) |  |
| 47 | Building | STU‑34 | Yes | Siemens | S7‑1200 (1214C‑DC/DC/DC) |  |
| 48 | Building | RB1‑1 | No | NA | NA |  |
| 49 | Building | RB1‑2 | No | NA | NA |  |
| 50 | Building | RB1‑3 | No | NA | NA |  |
| 51 | Building | RB1‑4 | No | NA | NA |  |
| 52 | Building | RB1‑5 | No | NA | NA |  |
| 53 | Building | RB1‑6 | No | NA | NA |  |
| 54 | Building | STU‑35 | Yes |  |  | New Machine |
| 55 | Building | STU‑36 | Yes |  |  | New Machine |
| 56 | Building | RB1‑7 | Yes |  |  | New Machine |
| 57 | Building | RB1‑8 | Yes |  |  | New Machine |
| 58 | Building | RB1‑9 | Yes |  |  | New Machine |
| 59 | Curing | K‑12 | Yes |  |  | New Machine |
| 60 | Curing | K‑13 | Yes |  |  | New Machine |
| 61 | Curing | O‑21 | Yes |  |  | New Machine |
| 62 | Curing | O‑22 | Yes |  |  | New Machine |
| 63 | Curing | O‑23 | Yes |  |  | New Machine |
| 64 | Curing | Q‑21 | Yes |  |  | New Machine |
| 65 | Curing | Q‑22 | Yes |  |  | New Machine |
| 66 | Curing | Q‑23 | Yes |  |  | New Machine |
| 85 | Balancing | Balancing‑1 | Yes | Allen‑Bradley | CompactLogix (L18ERM) |  |
| 86 | Balancing | Balancing‑2 | Yes | Allen‑Bradley | CompactLogix (L27ERM‑QBFC1B) |  |
| 87 | Balancing | Balancing‑3 | Yes | Allen‑Bradley | CompactLogix (L27ERM‑QBFC1B) |  |
| 88 | Balancing | Balancing‑4 | Yes | Allen‑Bradley | CompactLogix (L27ERM‑QBFC1B) |  |
| 89 | Balancing | Balancing‑5 | Yes | Allen‑Bradley | CompactLogix (L27ERM‑QBFC1B) |  |
| 90 | Balancing | Balancing‑6 | Yes | Allen‑Bradley | CompactLogix (L18ERM) |  |
| 91 | Balancing | Balancing‑7 | Yes | Allen‑Bradley | CompactLogix (L18ERM) |  |
| 92 | Balancing | Balancing‑8 | Yes | Allen‑Bradley | CompactLogix (L27ERM‑QBFC1B) |  |
| 93 | Balancing | Balancing‑9 | Yes | Allen‑Bradley | CompactLogix (L27ERM‑QBFC1B) |  |
| 94 | Balancing | Balancing‑10 | Yes | Allen‑Bradley | CompactLogix (L27ERM‑QBFC1B) |  |
| 95 | Runout | Runout‑1 | Yes | Mitsubishi | FX5U‑64M |  |
| 96 | Runout | Runout‑2 | Yes | Mitsubishi | FX5U‑64M |  |
| 97 | Runout | Runout‑3 | Yes | Mitsubishi | FX3G‑60M |  |
| 98 | Runout | Runout‑4 | Yes | Mitsubishi | FX3U‑64M |  |
| 99 | Runout | Runout‑5 | Yes | Mitsubishi | FX3U‑64M |  |
| 100 | Runout | Runout‑6 | Yes | Omron | NJ101 |  |
| 101 | Runout | Runout‑7 | Yes | Omron | NJ101 |  |
| 102 | Runout | Runout‑8 | Yes | Omron | NJ101 |  |
| 103 | Runout | Runout‑9 | Yes | Omron | NJ101 |  |
| 104 | Runout | Runout‑10 | Yes | Omron | NJ101 |  |
| 105 | Runout | Runout‑11 | Yes | Omron | NJ101 |  |
| 106 | 2nd Line Inspection | Inspection‑1 |  |  |  | Future Planning |
| 107 | 2nd Line Inspection | Inspection‑2 |  |  |  | Future Planning |
| 108 | 2nd Line Inspection | Inspection‑3 |  |  |  | Future Planning |
| 109 | 2nd Line Inspection | Inspection‑4 |  |  |  | Future Planning |
| 110 | 2nd Line Inspection | Inspection‑5 |  |  |  | Future Planning |
| 111 | 2nd Line Inspection | Inspection‑6 |  |  |  | Future Planning |
| 112 | 2nd Line Inspection | Inspection‑7 |  |  |  | Future Planning |
| 113 | 2nd Line Inspection | Inspection‑8 |  |  |  | Future Planning |
| 114 | 2nd Line Inspection | Inspection‑9 |  |  |  | Future Planning |
|  | Total |  | 103 |  |  |  |

Table: Unit‑4 machine and control system details

The interfacing approach recommended for each controller family in Unit‑4 is given below.

| PLC Family | Machines | Qty | Existing Communication | Recommended Hardware | Kepware Driver | Remarks |
| --- | --- | --- | --- | --- | --- | --- |
| Siemens S7‑300 (CPU 313C‑2DP, 315‑2DP) | CFE‑1, CFE‑2, 2 Roll Calender, Bias Cutter | 12 | MPI / Profibus DP | CP343‑1 Ethernet Communication Processor | Siemens TCP/IP Ethernet | Preferred OEM Ethernet interface for S7‑300. |
| Siemens S7‑1200 (CPU 1214C) | STU‑32, STU‑33, STU‑34, CFE‑2 (1214PN) | 4 | Built‑in Ethernet (Profinet) | Industrial NAT Device | Siemens TCP/IP Ethernet | Use built‑in Ethernet. NAT provides network isolation and avoids IP conflicts. |
| Siemens S7‑200 (CPU 224 DC/DC/DC) | Fabric Cutter (Multislitter) | 1 | PPI / RS485 | CP243‑1 Ethernet Module | Siemens S7‑200 Ethernet Driver | Preferred OEM Ethernet communication. |
| Mitsubishi FX2N (48MR / 64MR / 84MR) | Bead Winding‑2, STU‑1, STU‑3 to STU‑31, BTU‑16, BTU‑24 to BTU‑27 | 31 | RS232 | OEM Ethernet Communication Module | Mitsubishi Ethernet Driver | Legacy PLC; Ethernet enablement required. |
| Mitsubishi FX3G | Long Cutter, Runout‑3 | 2 | Serial | FX3G Ethernet Communication Adapter | Mitsubishi Ethernet Driver | Preferred OEM Ethernet interface. |
| Mitsubishi FX3U | Bead Winding‑1, Runout‑4, Runout‑5 | 3 | Serial | FX3U‑ENET Ethernet Adapter | Mitsubishi Ethernet Driver | Preferred OEM Ethernet interface. |
| Mitsubishi FX5U | STU‑2, Runout‑1, Runout‑2 | 3 | Built‑in Ethernet | Industrial NAT Device | Mitsubishi Ethernet Driver | Built‑in Ethernet retained; NAT for isolation. |
| Allen‑Bradley CompactLogix | Balancing‑1 to Balancing‑10 | 10 | Built‑in EtherNet/IP | Industrial NAT Device | Allen‑Bradley ControlLogix / CompactLogix Driver | No additional PLC module required. |
| Omron NJ101 | Runout‑6 to Runout‑11 | 6 | Built‑in EtherNet/IP | Industrial NAT Device | Omron NJ Ethernet Driver | Use built‑in Ethernet with network isolation. |
| New Machines | STU‑35, STU‑36, RB1‑7 to RB1‑9, Curing, etc. | 11 | TBD | To be finalised after OEM details | TBD | Communication details to be obtained after commissioning. |
| No PLC | RB1‑1 to RB1‑6 | 6 | NA | Digital I/O or machine retrofit | NA | Communication approach depends on machine design. |
| Total |  | 89 |  |  |  |  |

Table: Unit‑4 recommended interfacing approach by controller family

Reconciliation against the Unit‑4 equipment list:

- The table above covers 89 machines. Excluding the 9 2nd Line Inspection machines held under future planning, the Unit‑4 list contains 94 machines to be interfaced, so 5 machines are not yet covered by a recommendation.

- Siemens S7‑300: the equipment list contains 13 machines on CPU 313C‑2DP or 315‑2DP (CFE‑1 ×3, CFE‑2 ×3, 2 Roll Calender ×4, Bias Cutter ×3) against the 12 shown above. One machine is to be identified.

- Siemens S7‑1500: 2 Roll Calender ‑2 runs a CPU 1515‑2PN, for which no controller family is listed above. Built‑in Profinet with an industrial NAT device is assumed, in line with the S7‑1200 treatment, and is to be confirmed.

- New machines: the equipment list marks 14 machines as new (Fabric Cutter Multislitter, STU‑35, STU‑36, RB1‑7 to RB1‑9 and the 8 Curing machines) against the 11 shown above.

- Cold Feed Extruder‑2 (Extruder) is recorded in the equipment list as 313C‑2DP/1214PN and is counted above under S7‑1200. Whether this machine carries one controller or both is to be confirmed.

The manufacturer part numbers proposed against each controller model are given below. Final part selection is subject to survey of the installed hardware configuration of each machine.

| PLC Make | PLC Model | Recommended Hardware | Manufacturer Part No. | Kepware Support | Recommendation |
| --- | --- | --- | --- | --- | --- |
| Siemens | S7‑300 CPU 313C‑2DP | Ethernet Communication Processor | CP 343‑1 Lean (6GK7343‑1CX10‑0XE0) | Yes | ★★★★★ |
| Siemens | S7‑300 CPU 315‑2DP | Ethernet Communication Processor | CP 343‑1 Lean (6GK7343‑1CX10‑0XE0) | Yes | ★★★★★ |
| Siemens | S7‑1200 (1214C / 1214PN) | Industrial NAT Device | Moxa NAT‑102 or Hirschmann EAGLE One | Yes | ★★★★★ |
| Siemens | S7‑200 CPU 224 | Ethernet Module | CP243‑1 (6GK7243‑1EX01‑0XE0) | Yes | ★★★★★ |
| Mitsubishi | FX2N‑64MR / FX2N‑84MR | Ethernet Communication Adapter | FX2NC‑ENET‑ADP (or Mitsubishi‑supported equivalent) | Yes | ★★★★★ |
| Mitsubishi | FX3U‑64MR | Ethernet Adapter | FX3U‑ENET‑ADP | Yes | ★★★★★ |
| Mitsubishi | FX3G‑24M / 60M | Ethernet Adapter | FX3U‑ENET‑ADP (if supported by the FX3G configuration) | Yes | ★★★★☆ |
| Mitsubishi | FX5U | Industrial NAT Device | Moxa NAT‑102 | Yes | ★★★★★ |
| Allen‑Bradley | CompactLogix L18ERM / L27ERM | Industrial NAT Device | Moxa NAT‑102 | Yes | ★★★★★ |
| Omron | NJ101 | Industrial NAT Device | Moxa NAT‑102 | Yes | ★★★★★ |

Table: Unit‑4 proposed interfacing hardware part numbers

Industrial NAT devices are provided one per machine on the controllers that use their built‑in Ethernet port.

### Machine Connectivity Assessment

Based on the controller make and model declared in the machine data, the machines in scope are grouped into the following connectivity categories. This assessment is preliminary and shall be validated machine by machine during the Requirement Freeze & Workshop and Functional Design phases.

| Connectivity Category | Controller Types | Unit‑2 | Unit‑4 | Total | Data Acquisition Approach (Preliminary) |
| --- | --- | --- | --- | --- | --- |
| Ethernet / OPC capable | Siemens S7‑1200, S7‑1500; Mitsubishi FX5U; Allen‑Bradley CompactLogix; Omron NJ101 | 2 | 24 | 26 | Connected over the built‑in Ethernet port and read by Kepware OPC Server using the relevant native driver. No additional communication hardware required. |
| Serial / fieldbus only | Mitsubishi FX2N, FX3U, FX3G; Siemens S7‑300 (MPI / PROFIBUS‑DP), S7‑200; Allen‑Bradley SLC500 | 40 | 50 | 90 | An OEM Ethernet communication module is required on each PLC, after which the data is read by Kepware OPC Server using the relevant Ethernet driver. Refer to the note below. |
| PLC not available | RB1‑1 to RB1‑6 (Unit‑4 Building) | – | 6 | 6 | Data capture through manual entry or AIDC devices, unless a PLC is retrofitted by the customer / OEM. |
| New machines – controller to be confirmed | Unit‑4 Fabric Cutter, Building and Curing new machines | – | 14 | 14 | Connectivity requirement to be included in the OEM purchase specification. Assumed to be Ethernet / OPC UA capable. |
| Future scope | 2nd Line Inspection | – | 9 | 9 | Not considered in the current scope of this offer. |
| Total |  | 42 | 103 | 145 |  |

Table: Preliminary machine connectivity assessment

Notes and open points on machine data:

- 90 of the 145 machines carry controllers with serial or fieldbus interfaces only, with the existing RS232 port occupied by the HMI. Each of these machines requires an OEM Ethernet communication module to be fitted before the data can be read. Supply of materials and activities on existing field devices is presently listed under Exclusions in this document; the responsibility and commercial treatment of this hardware is to be agreed before the offer is finalised.

- The PLC make and model for 14 new machines (Unit‑4 Fabric Cutter Multislitter, STU‑35, STU‑36, RB1‑7 to RB1‑9 and the 8 Curing machines) are not yet available. Ethernet based connectivity with OPC UA is assumed for these machines and is to be confirmed by the respective OEMs.

- RB1‑1 to RB1‑6 have no PLC. The method of data capture for these machines is to be agreed with the customer.

- The Unit‑4 machine list has a break in serial numbers between S.No 66 and S.No 85. Details of the machines corresponding to S.No 67 to 84 have not been received and are not included in the 145 machines covered by this offer.

- AMCL‑7 and AMCL‑8 (Unit‑2) and the Cold Feed Extruder‑2 Skiver (Unit‑4) are undergoing refurbishment or upgradation. The final control system configuration of these machines is to be confirmed.

- The Unit‑4 list contains both a “2 Roll Calender ‑3” and a “3 Roll Calender ‑3” process area for what appear to be two parts of the same line. The naming is to be confirmed.

# Functional Details

## Solution Architecture

Machine data is acquired by Kepware OPC Server over an isolated industrial OT network and passed to the SmartMES server over OPC UA. Controllers with a built‑in Ethernet port connect directly through an industrial NAT device, which provides isolation and avoids IP conflicts with the existing machine networks. Legacy controllers are brought onto the same network through an OEM Ethernet communication module, as detailed in the Machine Details section. The Kepware and SmartMES layers are shown separately below; both run on the same application virtual machine, as set out in the IT Architecture section.

| SmartMES Server |  |  |
| --- | --- | --- |
| ▲ OPC UA |  |  |
| Kepware OPC Server |  |  |
| ▲ |  |  |
| Industrial OT Switch |  |  |
| ▲ |  |  |
| FX2N PLC OEM Communication Module | SLC500 PLC OEM Communication Module | FX5U PLC Built‑in Ethernet + NAT Device |

Figure: Unit‑2 data acquisition architecture

| SmartMES Server |  |  |  |
| --- | --- | --- | --- |
| ▲ OPC UA |  |  |  |
| Kepware OPC Server |  |  |  |
| ▲ |  |  |  |
| Industrial OT Switch |  |  |  |
| ▲ |  |  |  |
| Siemens S7 PLCs Legacy OEM Communication Module | Mitsubishi PLCs Legacy OEM Communication Module | Allen‑Bradley CompactLogix Built‑in Ethernet NAT Device | Omron NJ101 Built‑in Ethernet NAT Device |

Figure: Unit‑4 data acquisition architecture

## IT Architecture

The virtual machine estate below is already available with the customer, provisioned across a Production and a DR environment. It is reproduced here as the baseline for this offer; no change to the existing virtual machines is required.

| VM | Purpose | Server Type | OS | vCPU (2.4 GHz or above) | RAM (GB) | C Drive (GB) | D Drive (GB) |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Production |  |  |  |  |  |  |  |
| VM‑1 | TBM‑FF APP | VM | Windows Server 2022 | 12 | 64 | 256 | 512 |
| VM‑2 | Testing VM (UAT) | VM | Windows Server 2022 | 8 | 48 | 256 | 512 |
| VM‑3 | DB VM | VM | Windows Server 2022 | 16 | 192 | 256 | 2048 |
| VM‑4 | RMS‑TBM (Future) | VM | Windows Server 2022 | 12 | 64 | 256 | 512 |
| 10 % additional compute for future enhancement |  |  |  |  |  |  |  |
|  | Overall Required Resources |  |  | 48 | 368 | 1024 | 3584 |
| DR |  |  |  |  |  |  |  |
| VM‑1 | TBM‑FF APP | VM | Windows Server 2022 | 12 | 64 | 256 | 512 |
| VM‑2 | Testing VM (UAT) | VM | Windows Server 2022 | 8 | 48 | 256 | 512 |
| VM‑3 | DB VM | VM | Windows Server 2022 | 16 | 192 | 256 | 2048 |
| VM‑4 | RMS‑TBM (Future) | VM | Windows Server 2022 | 12 | 64 | 256 | 512 |
| 10 % additional compute for future enhancement |  |  |  |  |  |  |  |
|  | Overall Required Resources |  |  | 48 | 368 | 1024 | 3584 |

Table: Existing virtual machine estate – Production and DR

This project requires one additional application virtual machine, of the same specification as the existing application VM (VM‑1), to host SmartMES and the Kepware OPC Server for Unit‑2 and Unit‑4. The DR environment mirrors Production, so the same virtual machine is required in each.

| VM | Purpose | Server Type | OS | vCPU (2.4 GHz or above) | RAM (GB) | C Drive (GB) | D Drive (GB) |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Production |  |  |  |  |  |  |  |
| VM‑5 | SmartMES Application & Kepware OPC Server | VM | Windows Server 2022 | 12 | 64 | 256 | 512 |
| DR |  |  |  |  |  |  |  |
| VM‑5 | SmartMES Application & Kepware OPC Server | VM | Windows Server 2022 | 12 | 64 | 256 | 512 |
|  | Overall Additional Resources |  |  | 24 | 128 | 512 | 1024 |

Table: Additional virtual machines required for this project

Notes:

- The additional virtual machine is to be provided by the customer, in line with the infrastructure responsibilities set out in the Roles and Responsibilities section of this document.

- The Kepware OPC Server runs on this same application virtual machine; no separate virtual machine is required for it. As the machine carries both SmartMES and the OPC server polling the interfaced machines, its sizing is to be reviewed against the final tag count during Functional Design.

- With the additional virtual machine in place, the resource required in each environment becomes 60 vCPU, 432 GB RAM, 1280 GB of C drive and 4096 GB of D drive, and 120 vCPU, 864 GB RAM, 2560 GB of C drive and 8192 GB of D drive across Production and DR together.

- The existing Testing VM (UAT) and DB VM are assumed to be shared with this project rather than duplicated. Database sizing for SmartMES is to be reassessed against the existing DB VM after Functional Design sign off.

- Server sizing shall be reviewed once the machine count, tag count and data retention period are frozen during the Requirement Freeze and Functional Design phases.

# Scope Of Work

## Key Deliverables

## Scope Of Service

## Scope Of Supply

### Basis Of Supply

### Bill Of Material

The interfacing hardware quantities below follow from the machine lists and the recommended interfacing hardware of the Machine Details section, with industrial NAT devices provided one per machine. Quantities are to be confirmed against a site survey of the installed hardware configuration before order placement.

| S.No | Item | Manufacturer Part No. | Unit‑2 | Unit‑4 | Total | Remarks |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | Ethernet communication adapter – Mitsubishi FX2N | FX2NC‑ENET‑ADP (or Mitsubishi‑supported equivalent) | 39 | 31 | 70 | Compatibility with the installed FX2N configuration to be verified per machine. |
| 2 | Ethernet adapter – Mitsubishi FX3U and FX3G | FX3U‑ENET‑ADP | – | 5 | 5 | FX3G applicability subject to the installed configuration. |
| 3 | Ethernet communication processor – Siemens S7‑300 | CP 343‑1 Lean (6GK7343‑1CX10‑0XE0) | – | 12 | 12 | Subject to the S7‑300 reconciliation; the equipment list shows 13 machines. |
| 4 | Ethernet module – Siemens S7‑200 | CP243‑1 (6GK7243‑1EX01‑0XE0) | – | 1 | 1 |  |
| 5 | EtherNet/IP adapter – Allen‑Bradley SLC500 | 1747‑AENTR | 1 | – | 1 |  |
| 6 | Industrial NAT device | Moxa NAT‑102 or Hirschmann EAGLE One | 2 | 23 | 25 | One per machine using its built‑in Ethernet port. A further unit is required if the S7‑1500 on 2 Roll Calender ‑2 is confirmed. |
| 7 | Kepware OPC Server licence | To be confirmed | TBC | TBC | TBC | Drivers required: Mitsubishi Ethernet, Allen‑Bradley Ethernet and ControlLogix/CompactLogix, Siemens TCP/IP Ethernet, Siemens S7‑200, Omron NJ. |
| 8 | Industrial OT network switches | To be confirmed | TBC | TBC | TBC | Quantity subject to the OT network design and panel locations. |

Table: Interfacing hardware bill of material

Basis and exclusions:

- The quantities cover the 114 machines that carry an existing controller – 42 in Unit‑2 and 72 in Unit‑4 – of which 89 take a communication module or adapter and 25 use their built‑in Ethernet port behind a NAT device.

- The 14 new machines in Unit‑4 are excluded, as their controllers are not yet known. Interfacing hardware for these machines is to be included in the respective OEM purchase specification, or added by change request once the details are available.

- RB1‑1 to RB1‑6 in Unit‑4 have no PLC and are excluded. The data capture method for these machines is to be agreed.

- The 9 2nd Line Inspection machines held under future planning are excluded.

- Supply, mounting and installation of this hardware on existing machines, and any consequent PLC programme change, are presently listed under Exclusions in this document. The quantities above are therefore stated as the requirement; the supply responsibility for these items is to be agreed before the offer is finalised.

- Server, storage, operating system, database and other infrastructure items are listed against the customer in the Roles and Responsibilities section and are not part of this bill of material.

In addition to the interfacing hardware above, shopfloor data capture devices are required at the machines where operators book material and production against the MES. Tyre building machines take one MES HMI and one Bluetooth scanner each; curing machines take a Bluetooth scanner. The quantities are set out below.

| S.No | Unit | Process Area | Machines | MES HMI | Bluetooth Scanner | Remarks |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | Unit‑2 | TBB Tyre Building | 29 | 29 | 29 | One MES HMI and one Bluetooth scanner per tyre building machine. |
| 2 | Unit‑2 | LCV Tyre Building | 13 | 13 | 13 | One MES HMI and one Bluetooth scanner per tyre building machine. |
| 3 | Unit‑4 | Building (tyre building machines) | 45 | 45 | 45 | One MES HMI and one Bluetooth scanner per tyre building machine. Includes STU‑35, STU‑36 and RB1‑7 to RB1‑9. |
| 4 | Unit‑4 | Curing | 8 | – | 8 | Bluetooth scanner only. Host device for these scanners to be confirmed. |
| 5 | Unit‑4 | CFE 1 and CFE 2 | 7 | – | – | Not included in the current scope. |
| 6 | Unit‑4 | 2 Roll and 3 Roll Calenders | 5 | – | – | Not included in the current scope. |
| 7 | Unit‑4 | Bias Cutter | 3 | – | – | Not included in the current scope. |
| 8 | Unit‑4 | Bead Winding | 2 | – | – | Not included in the current scope. |
| 9 | Unit‑4 | Fabric Cutter | 3 | – | – | Not included in the current scope. |
| 10 | Unit‑4 | Balancing | 10 | – | – | Not included in the current scope. |
| 11 | Unit‑4 | Runout | 11 | – | – | Not included in the current scope. |
| 12 | Unit‑4 | 2nd Line Inspection | 9 | – | – | Future planning; not considered in the current scope. |
|  | Total |  | 145 | 87 | 95 |  |

Table: Shopfloor data capture hardware requirement

Basis and open points:

- Quantities follow the requirement that tyre building machines carry an MES HMI and a Bluetooth scanner, and curing machines carry a Bluetooth scanner. Tyre building covers TBB and LCV Tyre Building in Unit‑2 and the Building area in Unit‑4, 87 machines in total.

- MES HMI and AIDC devices are listed against the customer in the Roles and Responsibilities section of this document and are not part of the Smart Controls scope of supply.

- The curing machines carry a scanner without an MES HMI. Whether these scanners pair to a shared HMI, a handheld terminal or an existing station is to be confirmed, as it affects both the device count and the booking workflow.

- RB1‑1 to RB1‑6 in Unit‑4 have no PLC. The MES HMI at these machines provides the manual data capture referred to in the Machine Details section.

- The process areas shown at nil above are not included in the current scope. If material tracking is required at extrusion, calendering, component preparation or finishing, the device count is to be extended by change request.

- Scanner model, HMI specification, mounting, power and wireless coverage are to be agreed during the Functional Design phase. Wireless access point coverage across the shopfloor is a customer responsibility.

# Roles And Responsibilities

| RACI Terms |  |  |
| --- | --- | --- |
| R | Responsible | Team who performs the activity. |
| A | Accountable | Team who should answer for the success/failure/quality and timeliness of action. |
| C | Consulted | Team who must be consulted before the action is performed. |
| I | Informed | Team who must be informed after the action is performed. |

## Overall RACI

| Area | Scope | Details | Owner | Remarks |
| --- | --- | --- | --- | --- |
| Infrastructure | Supply | Infrastructure For MES Usage |  | Specification recommendation by SCIL. Actual estimation shall be evaluated post FDS Sign off. |
|  |  | SIT, UAT and PROD | CUST |  |
|  | Supply | Infrastructure During Implementation |  |  |
|  |  | DEV | CUST |  |
|  | Supply | Network Components |  | Recommendation by SCIL. |
|  |  | Shopfloor OT and IT Network | CUST |  |
|  | Supply | Scanner, Printer, IPC, PDA |  | Actual estimation shall be evaluated post FDS Sign off. |
|  |  | Shopfloor MES HMI | CUST |  |
|  | Supply | Infrastructure Software License ( Database, OS, Antivirus, Monitoring tool etc) | CUST | Specification recommendation by SCIL. Database Actual estimation shall be evaluated post FDS Sign off. |
|  |  | PROD, SIT, UAT Servers | CUST |  |
|  |  | DEV | SCIL |  |
| Application | Supply | SmartMES Software License ( MES modules ) |  | Actual load and license shall be reevaluated post FDS Sign off. |
|  |  | PROD, SIT, UAT Servers | SCIL |  |
|  |  | DEV | SCIL |  |
|  | Supply | SmartMES Other License ( Curing SCADA, MES SCADA etc) | SCIL |  |
|  |  | PROD, SIT, UAT Servers | SCIL |  |
|  |  | DEV | SCIL |  |
|  | Service | Layer 2 - SCADA Software Implementation |  |  |
|  |  | TBM SCADA, CURING SCADA, PLANTWIDE SCADA | SCIL |  |
|  | Service | Layer 3 - MoM Software Implementation |  |  |
|  |  | MES | SCIL |  |
|  | Service | 3rd Party Integration (ERP, WMS, ASRS etc) |  |  |
|  |  | Integration and Development | CUST |  |

## Scope of Work RACI

| S.No | Phase | Area | Activity | SCIL | CUST | ECST |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | Requirement | Workshop | Requirement gathering workshops arrangement with all Stakeholders. | R | A | C |
| 2 | Requirement | Documentation | Business Requirement Document creation. | R | C | I |
| 3 | Requirement | Requirement Checkpoint. | Business Requirement Document Sign Off | C | A | R |
| 4 | Requirement | Documentation | User Acceptance Criteria creation | R | C | A |
| 5 | Designing | Workshop | Conference room pilot with process owners/ business heads on need basis. | R | A | C |
| 6 | Designing | Documentation | Data requirements and availability of all application and interfaces | C | A | R |
| 7 | Designing | Infrastructure | Server sizing & specification recommendation. | C | C | R |
| 8 | Designing | Hardware | AIDC (Scanner, printer, PDA etc ) specification recommendation . | C | C | R |
| 9 | Designing | Application | Overall Solution architecture document creation. | R | A | C |
| 10 | Designing | Application | Infrastructure architecture document creation. | R | A | C |
| 11 | Designing | Application | Database requirements & specifications | C | A | R |
| 12 | Designing | Documentation | Functional design documentation. | R | A | C |
| 13 | Designing | Documentation | Interface Control design documentation | R | A | C |
| 14 | Designing | Management | Cordination with all OEM's for disucssion and follow ICD. | C | C | R |
| 15 | Designing | Integration Checkpoint. | Interface Control design Sign Off. | C | A | R |
| 16 | Designing | Solution Checkpoint. | Functional design Sign Off. | C | A | R |
| 17 | Designing | Acceptance Checkpoint. | User Acceptance Criteria Sign Off. | C | A | R |
| 18 | Designing | Documentation | Traceability matrix against Requirement IDs | R | A | I |
| 19 | Development | Data | Master and transactional data template. | R | C | I |
| 20 | Development | Data | Master and transactional data availability in template. | I | C | R |
| 21 | Development | Data | Master Data upload. | R | C | I |
| 22 | SIT | Management | Readiness of all OEM's interfaces for Integration testing. | I | C | R |
| 23 | SIT | Demo | Demo of possible feature. | R | A | C |
| 24 | SIT | Demo | Demo feedback and acceptance. | R | A | C |
| 25 | Testing | Application | User Acceptance Criteria Testing | C | A | R |
| 26 | Testing | Documentation | UAT test plan | R | A | C |
| 27 | Testing | Documentation | UAT Sign off | C | A | R |
| 28 | Commissioning | Application | MES Products installation. | R | A | I |
| 29 | Commissioning | Infrastructure | VM, Database and other 3rd party application installation. | C | C | R |
| 30 | Commissioning | Infrastructure | Server mounting, Storage configuration, OS, Antivirus, Network Readiness in Datacentre. | C | C | R |
| 31 | Commissioning | Infrastructure | Backup Software if any | C | C | R |
| 32 | Commissioning | Documentation | SOP and user manual | R | C | I |
| 33 | Commissioning | Infrastructure | Infrastructure, Database, Backup monitoring tools installation. | I | C | R |
| 34 | Hyper Care | Infrastructure | VM/Server Monitoring - Manually monitor the availability and performance of the Virtual Machines using OEM provided management tools at periodic intervals. | I | C | R |
| 35 | Hyper Care | Application | DB Monitoring - Manually monitor the availability of the databases using OEM provided management tools at periodic intervals | R | A | I |
| 36 | Hyper Care | Infrastructure | Backup Monitoring - Monitor the failed backup jobs Backup software console at periodic intervals | I | C | R |
| 37 | Hyper Care | Application | Application Monitoring : Monitor the availability of applications | R | A | I |
| 38 | Hyper Care | Application | Performance Maintenance - configuration changes, clean-up environment, identify inefficient SQL queries, Perform scheduled database start-up/shutdown, Database recovery | R | A | I |
| 39 | Hyper Care | Application | DB Structural Maintenance - Table space, disk space, and temporary space management, Database object structural management, Maintain physical database layout | R | A | I |
| 40 | Hyper Care | Infrastructure | Network Monitoring System installation | I | C | R |
| 41 | Hyper Care | Infrastructure | VM, Server, OS, Antivirus, other software maintenance | I | C | R |

# Project Management

## Project Organization Structure

The project is organised in three tiers. A steering board owns the commercial and scope decisions, a project manager on each side runs the delivery, and the working teams carry out the activities set out in the Scope of Work RACI. Each party nominates its members at project kick‑off.

| Steering Board Smart Controls and Customer sponsors |  |  |
| --- | --- | --- |
| ▲ |  |  |
| Project Managers Smart Controls PM • Customer PM |  |  |
| ▲ |  |  |
| Smart Controls Delivery Team Solution architect, MES and SCADA engineers, interface engineer, test lead | Customer Core Team Process owners, IT and OT, maintenance, quality, key users | OEM and Third Party Machine OEMs, ERP, WMS and ASRS application owners |

Figure: Project organization structure

| Role | Party | Responsibility | Remarks |
| --- | --- | --- | --- |
| Steering Board | Both | Owns the business case, approves scope and commercial changes, resolves matters escalated by the project managers. | Meets at each phase gate and on escalation. |
| Project Manager – Smart Controls | SCIL | Runs delivery against the project plan, owns the deliverables, reports progress, raises and assesses change requests. | Single point of contact for Smart Controls throughout. |
| Project Manager – Customer | CUST | Owns customer side readiness, stakeholder availability, infrastructure and approvals, and coordinates the OEMs. | The commissioning manager named in the Customer Support section. |
| Solution Architect | SCIL | Owns the solution and interface design, the FDS and the ICD. | Engaged from requirement workshop through to go live. |
| MES and SCADA Engineers | SCIL | Configure and develop the Layer 2 and Layer 3 application, and perform unit and system integration testing. | Core of the development and SIT phases. |
| Interface and Connectivity Engineer | SCIL | Owns the machine connectivity, the OPC server configuration and the third party interfaces. | Works with the customer OT team and the machine OEMs. |
| Test Lead | SCIL | Owns the test plan, the traceability matrix and the defect log through SIT and UAT. | Supports the customer through user acceptance testing. |
| Process Owners and Key Users | CUST / ECST | Provide the requirements, validate the design, execute user acceptance testing and sign off the acceptance criteria. | One nominated key user per process area is recommended. |
| IT and OT Team | CUST | Provide servers, database, network and shopfloor connectivity, and support deployment across the environments. | Owns the items listed against the customer in the RACI. |
| Machine OEMs and Third Party Vendors | ECST | Provide machine interface details, and make the changes needed on their own equipment or applications. | Coordinated by the customer project manager. |

Table: Project roles and responsibilities

## Project Governance

Governance runs on a fixed rhythm of reviews, with the phase sign offs of the Scope of Work RACI as the decision points.

| Forum | Frequency | Participants | Agenda | Output |
| --- | --- | --- | --- | --- |
| Daily stand up | Daily | Working teams | Progress, next steps, immediate blockers. | Held during development, SIT and UAT. |
| Project review | Weekly | Project managers, work stream leads | Plan against actual, risks, issues, actions, change requests. | Minutes and action log circulated by Smart Controls. |
| Phase gate review | At each phase end | Project managers, solution architect, process owners | Deliverable walkthrough and formal sign off of BRD, FDS, ICD, UAT. | Acceptance follows the Acceptance Procedures section. |
| Steering board review | Monthly, and on escalation | Sponsors, project managers | Overall status, scope and commercial changes, escalations, decisions. | The escalation point named in the Change Request Procedure. |
| Change control | As raised | Project managers | Impact assessment and approval of change requests. | Follows the Change Request Procedure section. |

Table: Project governance forums

Reporting and escalation:

- Smart Controls issues a weekly status report covering progress against the project plan, deliverables completed, open risks and issues, and any decisions awaited from the customer.

- Issues are raised first between the project managers. Matters that cannot be resolved there, or that affect scope, schedule or commercials, are escalated to the steering board.

- A single risk and issue register is maintained for the project and reviewed at the weekly project review.

- Deliverables are accepted in writing at each phase gate, on the terms set out in the Acceptance Procedures section of this document.

## Project Phases and Deliverables

### Requirement Freeze & Workshop

Smart Controls Team to organize workshop to collect, understand, review, finalize and fine tune the software and hardware requirements. The workshop could be conducted online or at customer site.

Customer shall align all the required experts and resources during workshop to clarify and explain the requirements in detail. Customer shall arrange all 3rd party experts for the interface discussion if required to be integrated with required software.
Customer shall provide the User Acceptance Criteria (UAC) to Smart Controls for final acceptance of agreed requirements.

Smart Controls to create a final Business Requirement Document (BRD) at the end of the workshop to be considered as the final deliverables. Any deviation in requirement from the basis of the offer to follow “Change Request Procedure “section mentioned in this document.

Smart Controls and Customer shall calibrate on the scope of supply and service post requirement clarity and definition.

As per the requirement clarification and detailing, the final scope of supply and service, project timeline, Solution Architecture, IT Architecture to be re-evaluated. Any required modification to be mutually discussed and considered for project implementation.

Finalized BRD to be signed off by both the parties.

### Functional Design Session

Smart Controls team to design the solution as per the signed off BRD. The solution design to cover the functional details of requirements and process flow of solution.

Smart Controls shall engage customer as and when needed with to clarify and design the solution. Customer shall align all required stakeholder to define and contribute to the solution designing process.

Smart Controls must document all the solution design in final Functional Design Specification (FDS) Document explaining the to be developed/configured functional design of the software.

Smart Controls must document the required interfaces with any 3rd party software as per the requirement and solution in Interface Control Design (ICD) Document.

At the end of Functional Design session, the final FDS and ICD must be signed off with both the parties (Smart Controls and Customer) before the development is proceeded. Customer shall provide the User Acceptance criteria sign off for final acceptance of agreed requirements and solution.

### System Integrated Testing (SIT)

During the software build and development Smart Controls team to perform the system integrate testing with all the modules developed and integrated with 3rd party system if any.

The developed modules will be deployed in SIT Server for demonstrations.

Smart Controls shall demonstrate the developed modules of the solution with integrating with 3rd party software if any.

Customer shall align all required stakeholder to understand and provide comments on developed modules. At the end of SIT, the modules will be demoed, and comments will be recorded.

### User Acceptance Testing (UAT)

After completion of SIT, the software will be deployed in UAT Server for final acceptance testing. All the required machines/3rd party software will be integrated with as like Production environment.

Smart Controls must deploy all the modules and integrate with actual devices. Customer shall perform system validation, executing User Acceptance Criteria to validate requirements delivery and system functionality.

Smart Controls will respond to issues and concerns raised during the validation stage.

Customer shall align all required stakeholder/Hardware/Server to perform the final test and accept the developed modules against the UAC.

At the end of UAT, the UAT will be Signed off by both parties and system will be accepted to go live.

### Commissioning & Go Live

After completion of UAT, the software will be deployed in Production Server.

All the required machines/3rd party software will be integrated as per UAT sign off. Smart Controls must deploy all the modules and integrate with devices/software. Smart Controls will provide the user manual videos to the end user to understand the system for usability.

Customer shall align all required stakeholder/Hardware/Server to deploy the solution on production server.

At the end of Commissioning and Go Live, the developed modules will be available to be used for respected end user.

### Rollout and Handover

Once the modules are commissioned and live in production server, the software will be under hyper care by Project team. In this hyper care duration system will be monitored for performance, functionality and bugs. Any bugs /improvement points identified will be fixed/improved by the project team.

Smart Controls will provide the all-user manual videos to the end user to understand the complete system for usability.

At the end of Rollout and Handover, the developed modules will be handed over to customer with required functional training videos.

## Project Timelines

The project is planned over 39 weeks, that is 9 months from kick‑off. The schedule below shows the service and supply streams against month bands M1 to M9, with the start week and duration of each activity.

| S.No | Scope | Activity | Start Wk | Dur. Wk | M1 | M2 | M3 | M4 | M5 | M6 | M7 | M8 | M9 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Service | Requirement Workshop and Business Requirement Document (BRD) | 1 | 3 |  |  |  |  |  |  |  |  |  |
| 2 |  | Solution Designing – Functional Design Specification (FDS) | 4 | 5 |  |  |  |  |  |  |  |  |  |
| 3 |  | Interface Designing – Interface Control Document (ICD) | 5 | 4 |  |  |  |  |  |  |  |  |  |
| 4 |  | Solution Development and Demonstration (DEMO) | 9 | 12 |  |  |  |  |  |  |  |  |  |
| 5 |  | System Integration Testing (SIT) | 19 | 5 |  |  |  |  |  |  |  |  |  |
| 6 |  | User Acceptance Testing (UAT) | 24 | 5 |  |  |  |  |  |  |  |  |  |
| 7 |  | Commissioning and Go Live | 29 | 3 |  |  |  |  |  |  |  |  |  |
| 8 |  | Hyper Care | 32 | 6 |  |  |  |  |  |  |  |  |  |
| 9 |  | Project Handover | 38 | 2 |  |  |  |  |  |  |  |  |  |
| 10 | Supply | Bill of Material finalisation and procurement | 2 | 2 |  |  |  |  |  |  |  |  |  |
| 11 |  | Material delivery | 4 | 6 |  |  |  |  |  |  |  |  |  |
| 12 |  | Material readiness and staging | 10 | 4 |  |  |  |  |  |  |  |  |  |
| 13 |  | Interfacing hardware installation and commissioning | 14 | 8 |  |  |  |  |  |  |  |  |  |

Table: Project timeline – 9 months from kick‑off

Basis of the schedule:

- Week 1 is the project kick‑off week. All dates are working weeks and assume the customer stakeholders, third party OEMs and site access are available as set out in the Roles and Responsibilities section.

- The schedule is driven by the sign off checkpoints. BRD sign off at the end of week 3, FDS and ICD sign off at the end of week 8, and UAT sign off at the end of week 28 are the gates for the following phase. A delay at any gate moves the remaining schedule by the same period.

- Interfacing hardware is procured and delivered in parallel with design and development, and is installed and commissioned between weeks 14 and 21, so that machine data is available before User Acceptance Testing begins in week 24.

- Material delivery of 6 weeks assumes the interfacing hardware in the Bill of Material is available on standard lead times. Imported items on extended lead times would move the commissioning window and, with it, the testing phases.

- Machines that are new or under refurbishment, and the machines still to be reconciled in Unit‑4, are to be available for interfacing before the commissioning window closes. Machines handed over later are addressed by change request.

- Hyper Care runs for 6 weeks after Go Live, followed by handover. A longer hyper care or an extended support period can be offered separately.

# Project Understanding

## General Assumptions

- The language for project, training, operator’s documentation, and user interface will be English.

- Customer is responsible to perform system validation, including developing and executing test cases (User Acceptance Test) to validate requirements and system functionality. Smart Controls will respond to issues and concerns raised during the validation stage.

- The overall project schedule shall be mutually agreed between Customer and Smart Controls at the beginning of the project, based on the contractual project schedule.

- Change request development will be done in Smart Controls premises and commissioning will be done on customer site.

- The complete job will be done remotely and onsite as per the project phase and SCIL decision for project completion.

- If Customer not able to supply any required facilities, resources, assistance or information in a timely manner, corresponding additional man days to complete these activities will be charged to customer on a time and materials basis using SmartControls standard rates in effect from time to time for any resulting additional work or waiting time.

## Project Assumptions

- If Customer not able to supply any required facilities, resources, assistance or information in a timely manner, Smart Controls shall be allowed corresponding additional man days to complete its activities.

- The overall project schedule shall be mutually agreed between Customer and Smart Controls at the beginning of the project.

- Smart Controls won’t be responsible for any third‑party software, solution, or hardware.

- The project deployment and commissioning will be done remotely with the support resources in plant. This change is applicable for all the areas in the plant.

- The reports will be available for those areas which are considered in the scope.

## Customer Support

Smart Controls would need the below support from Customer.

- Physical access to systems needed for commissioning.

- Customer will provide all the required Network to all the machines and PLC and servers.

- Customer will appoint a dedicated commissioning manager to be responsible to coordinate all the on‑site tasks and the communication between the parties (Smart Controls / Customer / OEMs).

- Any modification to be done on ERP / PLC / OEM’s or any third‑party Software will be taken care by Customer.

- Internet and MS Teams access has also to be available for Smart Controls team in the room.

- Ensure key person availability (e.g.: key users, IT persons) according to the project plan.

- Customer will provide all the information regarding business process, equipment, work procedures and plans which are required by Smart Controls to render the deliverables and will ensure that any information provided is accurate and complete.

- Additional compute power (CPU, RAM etc) on the existing MES servers for the new interfaces and requirements to be provided by the customer based on the recommendation from MES team.

- MS SQL Server standard version (Eight Core) / PostgreSQL.

- All the input required for the report must be available in the PLC / DB / CSV.

- Lodging, boarding and local conveyance at site.

- Separate room at site to be provided for the team to work.

## Exclusions

The following are excluded from the scope of Service of Smart Controls unless, otherwise explicitly mentioned in this document.

- Interface with any other supplier or third‑party hardware / software products and applications, or the process and tools.

- No Hardware / peripherals are considered for any of the machines.

- Mounting of all the hardware.

- Materials and activities on field devices and equipment (e.g., PLCs modification). Or modification of existing equipment for any process automation.

- Cloud instance and subscription.

- Any item not explicitly mentioned in this document.

- Network communication of machine PLC to the server.

- UPS power supply required for all the hardware.

- Network hardware for any reasons will be in JKIL.

- DHH scanners mounting accessory will be in JKIL.

# Change Request Procedure

Any deviation requested in this proposal OR during implementation OR post implementation phase in project will follow the below mentioned procedure. The standard change process can be graphically represented as follows:

This change process covers all major/minor changes. All change orders are submitted by the project management and quantified with respect to budget and time.

Both project managers must approve the change before the described activity may be performed. If no agreement between the project managers can be achieved, the change is not accepted. Each project manager can invoke the Steering Board for further decision.

Should any assumption set out or referred to in the proposal prove to be invalid or should fail to carry out any of your obligations under the proposal, Smart Controls will be entitled to equitable adjustments to the Services and to charge customer on a time and materials basis using Smart Controls standard rates in effect from time to time for any resulting additional work or waiting time.

## Change in Scope Of Service

| Stages | Responsible | Dependency | Action |
| --- | --- | --- | --- |
| Change Request | Customer | CR Approval. | Customer to document the required change in detail and provide all related master data and prerequisites. |
| Solutioning | Smart Controls | Customer to provide complete requirement details and all related prerequisites. | Smart Controls to perform impact analysis, code analysis and design the solution. The solution to be discussed and mutually agreed with Customer. |
| Building | Smart Controls | Customer to provide the acceptance criteria for the change. | Smart Controls to build the solution and preform unit testing and check acceptance criteria shared by Customer. |
| UAT | Customer | Smart Controls to deploy the solution on UAT Server. | Customer to test the solution in UAT server, perform impact and risk analysis and provide acceptance. |
| PROD | Smart Controls | Customer to provide the UAT acceptance. | Smart Controls to deploy the solution in PROD Server. |
| PROD | Smart Controls | Smart Controls to complete deployment. | Customer performs the acceptance testing in PROD Server. |

## Change in Scope Of Supply

| Stages | Responsible | Dependency | Action |
| --- | --- | --- | --- |
| Change Request | Customer | CR Approval. | Customer to document the required change in detail and provide related hardware specification details. |
| Solutioning | Smart Controls | Customer to provide complete requirement details and all related prerequisites. | Smart Controls to perform impact analysis and redesign the solution if needed. The solution/change/impact to be discussed and mutually agreed with Customer. |
| Procurement & Readiness | Smart Controls | Smart Controls and Customer to mutually agree to the change impact. | Smart Controls to procure the material as per CR and preform the required configurations on the hardware as per mutually agreed scope of work for the hardware. |
| UAT | Customer | Smart Controls to deploy the hardware on UAT Server. | Customer to test the hardware in UAT server and provide acceptance. |
| PROD | Smart Controls | Customer to provide the UAT acceptance. | Smart Controls to commission the hardware in PROD Server and performs the final acceptance testing. |

# Acceptance Procedures

## Notification of Deliverable Available Date

The approval of documents is given in writing; for other delivery units (e.g., system and training) an approval report is prepared. Acceptance will be confirmed in writing. The same process will be applicable for each deliverable of each milestone. Smart Controls is responsible to give Customer notification of the date when the deliverable as listed in project deliverables section will be available for acceptance by the Customer

## User Acceptance Tests

For the description of test cases, a form will be provided which is commonly agreed by the project manager from Smart Controls and the customer will be used.

## Inspection and Acceptance of Deliverables by Customer

Customer will notify Smart Controls in writing within five (5) working days following receipt of any milestone related deliverable for which Smart Controls has responsibility for delivery, if the deliverable fails to meet the acceptance criteria (if any) set out above. This notice shall state in reasonable detail and in a consolidated manner the reasons for a deliverable failing to meet such criteria.

Acceptance by the Customer shall not be unreasonably withheld. The passage of five (5) working days without notice of non-acceptance following delivery to Customer or the productive use by Customer of such deliverable shall constitute acceptance by the Customer.

If the notice of non-acceptance is not sufficiently detailed to allow Smart Controls to determine why such deliverable is unacceptable, Smart Controls may request in writing that the Customer provides sufficient additional information. The passage of five (5) working days from the date of such request without the provision of such additional information shall constitute acceptance of such deliverable by the Customer.

Smart Controls shall either rework such deliverable within fifteen (15) days after receipt of sufficient notice or present the Customer with a plan to rework the deliverable within a period of time that is reasonable under the circumstances.

Where the Scope of work does not set out acceptance criteria for any deliverable for which Smart Controls has responsibility for delivery, the deliverable will be deemed accepted on delivery to the Customer.

The project is completed if all deliverables as described are delivered to the Customer and accepted by the Customer via a formal Acceptance Document/email.

# Ownership Of Deliverables

- Pre-existing Software and Technology. Each party will retain all rights in any software, ideas, concepts, know-how, development tools, techniques or any other proprietary material or information that it owned or developed prior to the inception of a professional services project or acquired or developed thereafter without reference to or use of the intellectual property of the other party.

- Third Party Software and Technology. All software and technology that is licensed by a party from a third-party vendor will be and remain the property of such vendor.

- Deliverables Based on SmartControls Software and Technology. Subject to any third-party rights or restrictions, SmartControls will own all intellectual property rights in or related to all deliverables that are developed and delivered by SmartControls, provided that they consist of pre-existing SmartControls software or SmartControls software development tools, modifications thereto developed as part of the Services or works derived from pre-existing SmartControls software or SmartControls Tools developed as part of the Services.

- Deliverables Based on Customer’s Software and Technology. Subject to any third-party rights or restrictions, Customer shall own all intellectual property rights in or related to any deliverables that do not constitute pre-existing SmartControls software, SmartControls Tools, or modifications thereto or works derived therefrom, that are developed as part of the Services.

- The Services provided hereunder shall not constitute “works made for hire” under any applicable copyright laws. Ownership of work in progress under a Scope of Work shall remain with SmartControls until such time as title to a Deliverable transfer, if at all, in accordance with the signed Agreement.

- No License to Intellectual Property of the Other Party: No licenses will be deemed to have been granted by either party to any of its patents, copyrights, trade secrets or other intellectual property except as otherwise expressly provided in the Agreement. SmartControls will be free to use the ideas, concepts, methodologies, processes and know-how that are developed or created in the course of performing the Services provided that SmartControls does not use, or make reference to, the intellectual property or proprietary information of Customer.

# Annexure A – Commercial Scope

-----To be included ---